## Slide 1: Utility program
District 6 Breakout Session

## Slide 2: This Meeting is Being Recorded
Notes: HDR

## Slide 3: Welcome
Before we begin, let’s have a brief safety moment.
Virtual Attendees
Unmute yourself or use your chat box if you are in an emergency situation.
In-Person Attendees
Emergency Exits
Tornado Shelter
911 Caller
AED Location
Restrooms
Notes: HDR

## Slide 4: Agenda
Introductions
High Impact Project Review (by construction year)
Communication and Coordination
Questions and Wrap Up
Notes: HDR

## Slide 5: Introductions
Notes: All speakers introduce themselves briefly (Dave, section head, HDR facilitators); Attendees can introduce themselves if it’s a small group. If not – skip it!

## Slide 6: 2024 Utility policy
NDOT rolled out a new utility accommodation policy in 2024.
You can find more information, as well as a webinar about the changes, on the NDOT utility website at https://dot.nebraska.gov/business-center/utilities/.

## Slide 7: Outstanding Cy 2025
The following projects will likely not be completed in 2025

## Slide 8: Cozad Viaduct (MS) Project Number: STP-21-2(116) Control No: 61635
Project Length: 13.83
Scope of Work:
  Bridge Repair

## Slide 9: Cozad Viaduct (MS) Project Number: STP-21-2(116) Control No: 61635
Status: Construction
Right-of-way: In Progress
Construction Timing: 4/7/2025 - 12/13/2025

## Slide 10: Cozad Viaduct (MS) Project Number: STP-21-2(116) Control No: 61635
Anticipated Utilities Impact:
  Bridge Repair/Replace
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  No K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy
  Charter Communication
  City of Cozad
  Cozad Telephone Company
  Lumen
  Tallgrass Energy
  Cogent Communications
  Verizon

## Slide 12: Cy 2026
The following projects are anticipated to be let during 2026

## Slide 13: Halsey Spur Bridge Project Number: STP-FL-S86B(102) Control No: 61472
Project Length: 0.00
Scope of Work:
  Guardrail
  Bridge Replacement

## Slide 14: Halsey Spur Bridge Project Number: STP-FL-S86B(102) Control No: 61472
Status: Award Pending
Right-of-way: In Progress
Construction Timing: 3/23/2026- 10/24/2026

## Slide 15: Halsey Spur Bridge Project Number: STP-FL-S86B(102) Control No: 61472
Anticipated Utilities Impact:
  Bridge Repair/Replace
  Guardrail
Anticipated Request from Utilities:
  Provide Existing Locations
  Locates
Additional Information:
  No K-Sheets Required
  No Special Provisions Required
Utilities Involved:
  Consolidated Telephone Company
  Custer Public Power District

## Slide 17: Tryon South Project Number: STP-97-3(107) Control No: 61633
Project Length: 10.86
Scope of Work:
  Culvert Extension/Replacement
  Grading

## Slide 18: Tryon South Project Number: STP-97-3(107) Control No: 61633
Status: Design
Right-of-way: In Progress
Construction Timing: 6/22/2026 - 11/21/2026

## Slide 19: Tryon South Project Number: STP-97-3(107) Control No: 61633
Anticipated Utilities Impact:
  Culvert Extension/Replace
  Grading
Anticipated Request from Utilities:
  Provide Existing Locations
  Locates
  Potholing TBD
Additional Information:
  No K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Custer Public Power District
  Great Plains Communications

## Slide 21: NORTH PLATTE I-80 WIM SCALE Project Number: ITS-MISC-80-4(1042) Control No: 61764
Status: Preparing for Bid
Right-of-way:
Construction Timing: 4/1/2026 - 7/30/2026

## Slide 22: NORTH PLATTE I-80 WIM SCALE Project Number: ITS-MISC-80-4(1042) Control No: 61764
Project Length: 1.73
Scope of Work:
  Replace Scale
  Interstate ITS

## Slide 23: NORTH PLATTE I-80 WIM SCALE Project Number: ITS-MISC-80-4(1042) Control No: 61764
Anticipated Utilities Impact:
  Interstate ITS
  Replace Scale
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  Special Provisions Required
Utilities Involved:
  AT&T Communications
  Central Nebraska Public Power District
  Charter Communications
  City of North Platte
  Dawson Public Power District
  Lumen

## Slide 24: Cy 2027
The following projects are anticipated to be let during 2027

## Slide 25: In Lexington South Project Number: STP-283-2(108) Control No: 61733
Project Length: 2.23
Scope of Work:
  Culvert Extension/Replacement

## Slide 26: In Lexington South Project Number: STP-283-2(108) Control No: 61733
Status: Design
Right-of-way: In Progress
Construction Timing: 4/1/2027 - 10/31/2027

## Slide 27: In Lexington South Project Number: STP-283-2(108) Control No: 61733
Anticipated Utilities Impact:
Anticipated Request from Utilities:
Additional Information:
Utilities Involved:
  Black Hills Energy
  Charter Communications
  City of Lexington – Public Works & Electric
  Dawson County Public Power District
  Great Plains Communications
  Lumen
  Nebraska Public Power District
  OPTK Networks
  Tyson Foods
  Viaero Fiber Networks

## Slide 29: Leota – 1st St (NB), North Platte Project Number: NH-83-2(129) Control No: 61360
Project Length: 1.07
Scope of Work:
  Urban Reconstruction

## Slide 30: Leota – 1st St (NB), North Platte Project Number: NH-83-2(129) Control No: 61360
Status: Design
Right-of-way: In Progress
Construction Timing: 4/5/2027 - 11/18/2028

## Slide 31: Leota – 1st St (NB), North Platte Project Number: NH-83-2(129) Control No: 61360
Anticipated Utilities Impact:
  Urban Reconstruction
  Storm Sewer
  Electrical
  Traffic Signals
Anticipated Request from Utilities:
Additional Information:
Utilities Involved:
  Allo Communications
  Charter Communications
  City of North Platte
  Great Plains Regional Medical
  Lumen
  North Platte Public School
  Northwestern Energy
  OPTK Networks

## Slide 33: Maxwell South Project Number: STP-S56A(107) Control No: 61648
Project Length: 2.10
Scope of Work:
  Bridge Replacement

## Slide 34: Maxwell South Project Number: STP-S56A(107) Control No: 61648
Status: Design
Right-of-way: In Progress
Construction Timing: 4/1/2027 - 11/4/2028

## Slide 35: Maxwell South Project Number: STP-S56A(107) Control No: 61648
Anticipated Utilities Impact:
Anticipated Request from Utilities:
Additional Information:
Utilities Involved:
  AT&T
  Black Hills Energy
  Charter Communications
  City of Maxwell
  Consolidated Telecommunications
  Dawson Public Power District
  Great Plains Communications
  Nebraska Department of Water, Energy, and Environment
  OPTK Networks
  Pinpoint Communications
  Tallgrass Energy
  T-Mobile/Sprint
  Verizon
  Viaero Fiber

## Slide 37: D6 Fiber Connectivity Project Number: ITS-NH-83-2(145) Control No: 61767
Project Length: 3.05
Scope of Work:

## Slide 38: D6 Fiber Connectivity Project Number: ITS-NH-83-2(145) Control No: 61767
Status: Design
Right-of-way: Not Required
Construction Timing: 4/1/2027 - 10/31/2027

## Slide 39: D6 Fiber Connectivity Project Number: ITS-NH-83-2(145) Control No: 61767
Anticipated Utilities Impact:
  Fiber and Conduit Installation
Anticipated Request from Utilities:
Additional Information:
Utilities Involved:
  Allo Communications
  Charter Communications
  City of North Platte
  Great Plains Regional Medical Center
  Lumen
  North Platte Public School
  Northwestern Energy
  OPTK Networks
  Panhandle Geotech & Environmental
  Pinpoint Communications
  Village of Big Springs

## Slide 40: Berwyn - Ansley Project Number: NH-STP-2-3(130) Control No: 61703
Project Length: 8.51
Scope of Work:
  Pavement Repairs
  Bridge Repair

## Slide 41: Berwyn - Ansley Project Number: NH-STP-2-3(130) Control No: 61703
Status: Design
Right-of-way: In Progress
Construction Timing: 3/1/2027 - 10/31/2027

## Slide 42: Berwyn - Ansley Project Number: NH-STP-2-3(130) Control No: 61703
Anticipated Utilities Impact:
  Bridge Repair/Replace
Anticipated Request from Utilities:
  Provide Existing Locations
  Utilities Workshop
Additional Information:
  No K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy
  Custer Public Power District
  Hamilton Telecommunications
  Lumen
  Tallgrass Energy
  Viaero Fiber Network
  Village of Ansley

## Slide 44: TRYON WEST Project Number: STP-92-2(111) Control No: 61613
Project Length: 13.2
Scope of Work:
  Asphalt
  Shouldering
  Grading

## Slide 45: TRYON WEST Project Number: STP-92-2(111) Control No: 61613
Status:
Right-of-way: In Progress
Construction Timing: 4/10/2027 - 9/25/2027

## Slide 46: TRYON WEST Project Number: STP-92-2(111) Control No: 61613
Anticipated Utilities Impact:
  Asphalt
  Shouldering
  Grading
Anticipated Request from Utilities:
  Provide Existing Locations
Additional Information:
  Special Provisions Required
Utilities Involved:
  Great Plains Communications
  Custer Public Power District

## Slide 47: Questions & Wrap Up
Notes: HDR

## Slide 48: Any final Questions?
Ask them now!
If you have questions after this meeting, or would like to view more detailed project maps, please reach out to your utility coordinator.
Notes: HDR

## Slide 49: Have a Question about a project your Utility is involved in?
Contact your district’s utility coordinator!
Notes: HDR

## Slide 50: We need your feedback
Your valuable feedback helps these meetings – and NDOT’s utility coordination program – be better.
Use your phone’s camera to scan this QR code or use our paper survey.
Notes: HDR

## Slide 51: Visit our Website
Visit NDOT.info/utility for more information on:
Utility accommodation
Permitting
Coordination
Project information
Reimbursements
Additional information
Scan the QR Code to view the 2026 Program Book!
Notes: HDR

## Slide 52: Thank You
Notes: HDR