## Slide 1: Utility program
District 2 Breakout Session

## Slide 2: This Meeting is Being Recorded
Notes: HDR

## Slide 3: Welcome
Before we begin, let’s have a brief safety moment.
Virtual Attendees
Unmute yourself or use your chat box if you are in an emergency situation.
In-Person Attendees
Emergency Exits
Tornado Shelter
911 Caller
AED Location
Restrooms
Notes: HDR

## Slide 4: Agenda
Introductions
High Impact Project Review (by construction year)
Communication and Coordination
Questions and Wrap Up
Notes: HDR

## Slide 5: Introductions
Notes: All speakers introduce themselves briefly (Dave, section head, HDR facilitators); Attendees can introduce themselves if it’s a small group. If not – skip it!

## Slide 6: 2024 Utility policy
NDOT rolled out a new utility accommodation policy in 2024.
You can find more information, as well as a webinar about the changes, on the NDOT utility website at https://dot.nebraska.gov/business-center/utilities/.

## Slide 7: Cy 2026
The following projects are anticipated to be let during 2026

## Slide 8: US-275/72nd St. Interchange Project Number: NH-275-7(194) Control No: 22469
Project Length: 0.62
Scope of Work:
  Urban Reconstruction
  Full Depth Pavement
  Grading

## Slide 9: US-275/72nd St. Interchange Project Number: NH-275-7(194) Control No: 22469
Status: Design
Right-of-way: In Progress
Construction Timing: 9/15/2025 - 11/25/2026

## Slide 10: US-275/72nd St. Interchange Project Number: NH-275-7(194) Control No: 22469
Anticipated Utilities Impact:
  Urban Recon
  Full Depth Pavement
  Grading
Anticipated Request from Utilities:
  Coordination with NDOT
  Potholing TBD
  Provide Existing Locations
Additional Information:
Utilities Involved:
  AT&T Communications
  City of Omaha
  City of Ralston
  Cox Communications
  Great Plains Communications
  Lumen
  Verizon
  Metropolitan Utilities District
  Northern Natural Gas
  Omaha Public Power District
  Papio-Missouri Natural Resources District
  Pinpoint Communications

## Slide 11: Millard highlands along i-80 Project Number: NH-80-9(215) Control No: 22975
Project Length: 1.27 miles
Scope of Work:
  Grading
  Culverts

## Slide 12: Millard highlands along i-80 Project Number: NH-80-9(215) Control No: 22975
Status: Design
Right-of-way: In Progress
Construction Timing: 7/13/2026 - 10/31/2026

## Slide 13: Millard highlands along i-80 Project Number: NH-80-9(215) Control No: 22975
Anticipated Utilities Impact:
  Grading
  Culvert
Anticipated Request from Utilities:
  Coordination with NDOT
  Potholing TBD
  Provide Existing Locations
Additional Information:
Utilities Involved:
  Allo Communications
  AT&T Communications
  Black Hills Energy
  City of La Vista
  City of Omaha
  Cox Communications
  Great Plains Communications
  Lumen
  Verizon
  Metropolitan Utilities District
  Omaha Public Power District
  Segra

## Slide 14: Rawhide creek culvert Project Number: nh-30-6(140) Control No: 22720a
Project Length: 0.4
Scope of Work:
  Culvert Extension/Replacement
  Grading
  Full Depth Pavement

## Slide 15: Rawhide creek culvert Project Number: nh-30-6(140) Control No: 22720a
Status: Design
Right-of-way: Not Required
Construction Timing: 5/29/2026 - 11/28/2026

## Slide 16: Rawhide creek culvert Project Number: nh-30-6(140) Control No: 22720a
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  Full Depth Pavement
  Grading
Anticipated Request from Utilities:
  Coordination with NDOT
  Potholing TBD
  Provide Existing Locations
Additional Information:
Utilities Involved:
  Charter Communications
  City of Fremont
  Cox Communications
  Fastwyre
  Great Plains Communications
  Lumen
  Omaha Public Power District

## Slide 17: Louisville - springfield Project Number: stp-50-2(141) Control No: 22833
Project Length: 4.88
Scope of Work:
  Culvert Extension/Replacement
  Grading

## Slide 18: Louisville - springfield Project Number: stp-50-2(141) Control No: 22833
Status: Design
Right-of-way: Not Required
Construction Timing: 8/31/2026 - 11/28/2026

## Slide 19: Louisville - springfield Project Number: stp-50-2(141) Control No: 22833
Anticipated Utilities Impact:
  Culvert Extension/Replacement
  Grading
Anticipated Request from Utilities:
  Potholing TBD
  Provide Existing Locations
Additional Information:
Utilities Involved:
  Charter Communications
  City of Louisville
  City of Springfield
  Cogent Communications
  Cox Communications
  Great Plains Communications
  Lumen
  Metropolitan Utilities District
  OPTK Networks
  Northern Natural Gas
  Omaha Public Power District
  Segra
  Verizon
  Windstream Communications
  Zayo Group

## Slide 20: 132ND STREET– N-133 Project Number: STP-36-7(116) Control No: 22597
Project Length: 2.19
Scope of Work:
  Full Depth Pavement
  Resurfacing
  Bridge Repair

## Slide 21: 132ND STREET– N-133 Project Number: STP-36-7(116) Control No: 22597
Status: Design
Right-of-way: Not Required
Construction Timing: 7/27/2026 - 11/25/2026

## Slide 22: 132ND STREET– N-133 Project Number: STP-36-7(116) Control No: 22597
Anticipated Utilities Impact:
  Full Depth Pavement
  Bridge Repair/Replace
Anticipated Request from Utilities:
  Coordination with NDOT
  Potholing TBD
  Provide Existing Locations
Additional Information:
Utilities Involved:
  AT&T
  City of Bennington
  Cox Communications
  Fastwyre
  Lumen
  OneOK
  Metropolitan Utilities District
  OPTK Networks
  Omaha Public Power District
  Papio-Missouri River Natural Resources District
  Segra
  VYVE Broadband

## Slide 23: Elkhorn River – N-133 Project Number: STP-36-7(116) Control No: 22597

## Slide 24: D2-A High Mast Tower Repl. Project Number: STP-275-7(210) Control No: 22898
Project Length: 0.00 (4 interchanges)
Scope of Work:
  ITS/Lighting
  Grading

## Slide 25: D2-A High Mast Tower Repl. Project Number: STP-275-7(210) Control No: 22898
Status: Awarded
Right-of-way: Not Required
Construction Timing: 6/1/2026 - 11/25/2026

## Slide 26: D2-A High Mast Tower Repl. Project Number: STP-275-7(210) Control No: 22898
Anticipated Utilities Impact:
  Grading
Anticipated Request from Utilities:
  Provide Existing Locations
  Potholing TBD
Additional Information:
Utilities Involved:
  Black Hills Energy
  Omaha Public Power District
  City of Valley
  Great Plains Communications
  WelTel Systems
  Lumen

## Slide 27: D2-A High Mast Tower Repl. Project Number: STP-275-7(210) Control No: 22898

## Slide 28: Pacific - Dodge, Omaha Project Number: NH-MTIS-680-9(13) Control No: 22852
Project Length: 1.50
Scope of Work:
  Full Depth Pavement
  Grading
  Bridge Repair

## Slide 29: Pacific - Dodge, Omaha Project Number: NH-MTIS-680-9(13) Control No: 22852
Status: Design
Right-of-way: In Progress
Construction Timing: 4/1/2026 - 10/30/2026

## Slide 30: Pacific - Dodge, Omaha Project Number: NH-MTIS-680-9(13) Control No: 22852
Anticipated Utilities Impact:
  Full Depth Pavement
  Grading
  Bridge Repair/Replace
Anticipated Request from Utilities:
  Coordination with NDOT
  Potholing TBD
  Provide Existing Locations
Additional Information:
Utilities Involved:
  AT&T Communications
  City of Omaha
  Cox Communications
  Great Plains Communications
  Lumen
  Metropolitan Utilities District
  Omaha Public Power District
  Segra
  Verizon

## Slide 31: Pacific - Dodge, Omaha Project Number: NH-MTIS-680-9(13) Control No: 22852

## Slide 32: US-275 & W. Dodge Road Project Number: HSIP-275-7(209) Control No: 22888
Project Length: 0.00
Scope of Work:
  Urban Reconstruction
  Grading
  Culvert Extension/Replacement

## Slide 33: US-275 & W. Dodge Road Project Number: HSIP-275-7(209) Control No: 22888
Status: Design
Right-of-way: In Progress
Construction Timing: 7/13/2026 - 11/25/2026

## Slide 34: US-275 & W. Dodge Road Project Number: HSIP-275-7(209) Control No: 22888
Anticipated Utilities Impact:
  Urban Recon
  Grading
  Culvert Extension/Replace
Anticipated Request from Utilities:
  Coordination with NDOT
  Potholing TBD
  Provide Existing Locations
Additional Information:
Utilities Involved:
  Black Hills Energy
  Lumen
  Omaha Public Power District

## Slide 35: US-275 & W. Dodge Road Project Number: HSIP-275-7(209) Control No: 22888

## Slide 36: US-75 – NASHVILLE Project Number: MISC-75-3(1031) Control No: 22994
Project Length: 0.00
Scope of Work:
  Culvert Replacement
  Full-depth pavement

## Slide 37: US-75 – Nashville Project Number: MISC-75-3(1031) Control No: 22994
Status: Design
Right-of-way: In Progress
Construction Timing: TBD

## Slide 38: US-75 – NASHVILLE Project Number: MISC-75-3(1031) Control No: 22994
Anticipated Utilities Impact:
  Culvert Extension/Replace
Anticipated Request from Utilities:
  Coordination with NDOT
  Potholing TBD
  Provide Existing Locations
Additional Information:
Utilities Involved:
  Cox Communications
  Lumen
  Metropolitan Utilities District
  Omaha Public Power District
  Washington County Rural Water District #1

## Slide 39: I-80 Drainage at 96th Street Project Number: MISC-80-9(1223) Control No: 22950
Project Length: 0.15
Scope of Work:
  Grading
  Culvert Extension/Replacement

## Slide 40: I-80 Drainage at 96th Street Project Number: MISC-80-9(1223) Control No: 22950
Status: Design
Right-of-way: In Progress
Construction Timing: 9/28/2026 - 10/10/2026

## Slide 41: I-80 Drainage at 96th Street Project Number: MISC-80-9(1223) Control No: 22950
Anticipated Utilities Impact:
  Grading
  Culvert Extension/Replace
Anticipated Request from Utilities:
  Coordination with NDOT
  Potholing TBD
  Provide Existing Locations
Additional Information:
  Declared emergency project
Utilities Involved:
  AT&T Communications
  City of Omaha
  Metropolitan Utilities District
  Omaha Public Power District
  OneOK
  Verizon

## Slide 42: Cy 2027
The following projects are anticipated to be let during 2027

## Slide 43: District 2 & District 1 Fiber Cleanup Project Number: ITS-NH-D2(120) Control No: 22967
Project Length: 4.36
Scope of Work:
  Miscellaneous

## Slide 44: District 2 & District 1 Fiber Cleanup Project Number: ITS-NH-D2(120) Control No: 22967
Status: Design
Right-of-way: Not Required
Construction Timing: 4/1/2027- 10/31/2027

## Slide 45: District 2 & District 1 Fiber Cleanup Project Number: ITS-NH-D2(120) Control No: 22967
Anticipated Utilities Impact:
Anticipated Request from Utilities:
Additional Information:
Utilities Involved:
  Allo Communications
  AT&T Communications
  Black Hills Energy
  City of Gretna
  City of Omaha
  Cox Communications
  Great Plains Communications
  Lumen
  Metropolitan Utilities District
  Northern Natural Gas
  Omaha Public Power District
  Sarpy County
  Segra
  Verizon
  Windstream Communications
  Zayo Group

## Slide 46: District 2 & District 1 Fiber Cleanup Project Number: ITS-NH-D2(120) Control No: 22967

## Slide 47: 50th St- I-480, Omaha Project Number: NH-MTIS-80-9(203) Control No: 22855
Project Length: 2.06
Scope of Work:
  Bridge Repair/Redecking
  Culvert Extension/Replacement
  Full Depth Pavement
  Potential Noise Wall (to be determined)

## Slide 48: 50th St- I-480, Omaha Project Number: NH-MTIS-80-9(203) Control No: 22855
Status: Design
Right-of-way: In Progress
Construction Timing: 4/1/2027 - 10/31/2028

## Slide 49: 50th St- I-480, Omaha Project Number: NH-MTIS-80-9(203) Control No: 22855
Anticipated Utilities Impact:
Anticipated Request from Utilities:
Additional Information:
Utilities Involved:
  AT&T Communications
  City of Omaha
  Cogent Communications
  Cox Communications
  Lumen
  Metropolitan Utilities District
  Omaha Public Power District
  Verizon

## Slide 50: WB I-80 Bridge at I-680 Project Number: NH-80-9(216) Control No: 22980
Project Length: 0.00
Scope of Work:
  Bridge Repair
  Guardrail

## Slide 51: WB I-80 Bridge at I-680 Project Number: NH-80-9(216) Control No: 22980
Status: Design
Right-of-way: Not Required
Construction Timing: 4/1/2027- 10/31/2027

## Slide 52: WB I-80 Bridge at I-680 Project Number: NH-80-9(216) Control No: 22980
Anticipated Utilities Impact:
Anticipated Request from Utilities:
Additional Information:
Utilities Involved:
  City of Omaha
  Metropolitan Utilities District
  Omaha Public Power District

## Slide 53: N-66 Connection in Louisville Project Number: STP-66-7(119) Control No: 22795
Project Length: 0.54
Scope of Work:
  Full Depth Pavement
  Urban Reconstruction
  Miscellaneous

## Slide 54: N-66 Connection in Louisville Project Number: STP-66-7(119) Control No: 22795
Status: Design
Right-of-way: In Progress
Construction Timing: 3/29/2027 - 11/24/2027

## Slide 55: N-66 Connection in Louisville Project Number: STP-66-7(119) Control No: 22795
Anticipated Utilities Impact:
  Full Depth Pavement
  Urban Recon
Anticipated Request from Utilities:
  Coordination with NDOT
  Provide Existing Locations
  Potholing TBD
Additional Information:
Utilities Involved:
  Black Hills Energy
  Charter Communications
  City of Louisville
  Omaha Public Power District
  OPTK Networks
  Segra
  Windstream Communications

## Slide 56: N-66 Connection in Louisville Project Number: STP-66-7(119) Control No: 22795

## Slide 57: I-80, Sarpy County Interchange Project Number: NH-MTIS-80-9(131) Control No: 22917
Project Length: 0.0
Scope of Work:
  Full Depth Pavement
  Urban Reconstruction

## Slide 58: I-80, Sarpy County Interchange Project Number: NH-MTIS-80-9(131) Control No: 22917
Status: Design
Right-of-way: In Progress
Construction Timing: 4/1/2027-10/31/2028

## Slide 59: I-80, Sarpy County Interchange Project Number: NH-MTIS-80-9(131) Control No: 22917
Anticipated Utilities Impact:
  Full Depth Pavement
  Urban Recon
Anticipated Request from Utilities:
  Coordination with NDOT
  Provide Existing Locations
  Potholing TBD
Additional Information:
Utilities Involved:
  City of Omaha
  Cox Communications
  Fastwyre Broadband
  Great Plains Communications
  Lumen
  Metropolitan Utilities District
  Omaha Public Power District
  OneOK
  OPTK Networks
  Segra
  Verizon
  Windstream
  Zayo Group

## Slide 60: Cy 2028
The following projects are anticipated to be let during 2028

## Slide 61: Elkhorn Viaduct Project Number: NH-31-2(114) Control No: 22636
Project Length: 0.28
Scope of Work:
  Bridge Replacement
  Full Depth Pavement
  Grading

## Slide 62: Elkhorn Viaduct Project Number: NH-31-2(114) Control No: 22636
Status: Design
Right-of-way: In Progress
Construction Timing: TBD 2028

## Slide 63: Elkhorn Viaduct Project Number: NH-31-2(114) Control No: 22636
Anticipated Utilities Impact:
  Bridge Repair/Replace
  Full Depth Pavement
  Grading
Anticipated Request from Utilities:
  Coordination with NDOT
  Provide Existing Locations
  Potholing TBD
Additional Information:
Utilities Involved:
  Black Hills Energy
  Charter Communications
  City of Louisville
  Great Plains Communications
  OneOK
  Northern Natural Gas
  Omaha Public Power District
  OPTK Networks
  Otoe County Rural Water District 3
  Segra
  Verizon
  Village of Manley
  Windstream Communications
  Zayo Group

## Slide 64: Elkhorn Viaduct Project Number: NH-31-2(114) Control No: 22636

## Slide 65: Questions & Wrap Up
Notes: HDR

## Slide 66: Any final Questions?
Ask them now!
If you have questions after this meeting, or would like to view more detailed project maps, please reach out to your utility coordinator.
Notes: HDR

## Slide 67: Have a Question about a project your Utility is involved in?
Contact your district’s utility coordinator!
Notes: HDR

## Slide 68: We need your feedback
Your valuable feedback helps these meetings – and NDOT’s utility coordination program – be better.
Use your phone’s camera to scan this QR code or use our paper survey.
Notes: HDR

## Slide 69: Visit our Website
Visit NDOT.info/utility for more information on:
Utility accommodation
Permitting
Coordination
Project information
Reimbursements
Additional information
Scan the QR Code to view the 2026 Program Book!
Notes: HDR

## Slide 70: Thank You
Notes: HDR

## Slide 71: Outstanding Cy 2025
The following projects will likely not be completed in 2025

## Slide 72: I-480 Missouri River Bridge Project Number: NH-480-9(11) Control No: 22807
Project Length: 0.00
Scope of Work:
  Bridge Repair
  Pavement Repairs
  Miscellaneous

## Slide 73: I-480 Missouri River Bridge Project Number: NH-480-9(11) Control No: 22807
Status: Construction
Right-of-way: Not Required
Construction Timing: 9/23/2024 - 10/31/2026

## Slide 74: I-480 Missouri River Bridge Project Number: NH-480-9(11) Control No: 22807
Anticipated Utilities Impact:
  Bridge Repair/Replace
Anticipated Request from Utilities:
  Coordination with NDOT
Additional Information:
Utilities Involved:

## Slide 75: I-480 Missouri River Bridge Project Number: NH-480-9(11) Control No: 22807

## Slide 76: D2-B High Mast Tower Repl. Project Number: STP-680-9(44) Control No: 22899
Project Length: 5.00
Scope of Work:
  ITS/Lighting
  Grading

## Slide 77: D2-B High Mast Tower Repl. Project Number: STP-680-9(44) Control No: 22899
Status: Award Pending
Right-of-way: Not Required
Construction Timing: 2/3/2025 - 11/26/2025

## Slide 78: D2-B High Mast Tower Repl. Project Number: STP-680-9(44) Control No: 22899
Anticipated Utilities Impact:
  Urban Recon
Anticipated Request from Utilities:
  Provide Existing Locations
  Potholing Required
Additional Information:
Utilities Involved:
  AT&T Communications
  City of Omaha
  Cox Communications
  Great Plains Communications
  Lumen
  Metropolitan Utilities District
  Omaha Public Power District
  OneOK
  Segra
  Verizon
  Windstream Communications

## Slide 79: D2-B High Mast Tower Repl. Project Number: STP-680-9(44) Control No: 22899

## Slide 80: D2-C High Mast Tower Repl. Project Number: STP-680-9(43) Control No: 22900
Project Length: 3.00
Scope of Work:
  ITS/Lighting
  Grading

## Slide 81: D2-C High Mast Tower Repl. Project Number: STP-680-9(43) Control No: 22900
Status: Award Pending
Right-of-way: Not Required
Construction Timing: 4/7/2025 - 6/6/2026

## Slide 82: D2-C High Mast Tower Repl. Project Number: STP-680-9(43) Control No: 22900
Anticipated Utilities Impact:
  Urban Recon
Anticipated Request from Utilities:
  Provide Existing Locations
  Potholing Required
Additional Information:
Utilities Involved:
  City of Omaha
  Cox Communications
  Fastwyre Broadband
  Great Plains Communications
  Lumen
  Metropolitan Utilities District
  Omaha Public Power District
  OneOK
  Segra
  Verizon

## Slide 83: D2-C High Mast Tower Repl. Project Number: STP-680-9(43) Control No: 22900

## Slide 84: N-50 / N-31 Intersection Project Number: STP-50-2(140) Control No: 22805
Project Length: 0.00
Scope of Work:
  Full Depth Pavement

## Slide 85: N-50 / N-31 Intersection Project Number: STP-50-2(140) Control No: 22805
Status: Award Pending
Right-of-way:
Construction Timing: 4/1/2025 - 10/31/2025

## Slide 86: N-50 / N-31 Intersection Project Number: STP-50-2(140) Control No: 22805
Anticipated Utilities Impact:
  Full Depth Pavement
Anticipated Request from Utilities:
  Provide Existing Locations
  Potholing Required
Additional Information:
Utilities Involved:
  Charter Communications
  City of Louisville
  Lumen
  Omaha Public Power District
  OPTK Networks
  Segra
  Verizon
  Windstream Communications
  Zayo Group

## Slide 87: N-50 / N-31 Intersection Project Number: STP-50-2(140) Control No: 22805

## Slide 88: US-275 / N-92 Culvert Project Number: NH-HSIP-275-7(1047) Control No: 22892
Project Length: 0.00
Scope of Work:
  Culvert Extension/Replacement
  Grading

## Slide 89: US-275 / N-92 Culvert Project Number: NH-HSIP-275-7(1047) Control No: 22892
Status: Design
Right-of-way:
Construction Timing: 6/10/2025 - 7/24/2025

## Slide 90: US-275 / N-92 Culvert Project Number: NH-HSIP-275-7(1047) Control No: 22892
Anticipated Utilities Impact:
  Culvert Extension/Replace
  Grading
Anticipated Request from Utilities:
  Provide Existing Locations
  Potholing Required
  Coordination with NDOT
Additional Information:
Utilities Involved:
  Cox Communications
  Great Plains Communications
  Lumen
  Metropolitan Utilities District
  Omaha Public Power District

## Slide 91: US-275 / N-92 Culvert Project Number: NH-HSIP-275-7(1047) Control No: 22892

## Slide 92: Union – Murray Project Number: NH-34-7(129) Control No: 22543
Project Length: 7.24
Scope of Work:
  Resurfacing
  Bridge Repair

## Slide 93: Union – Murray Project Number: NH-34-7(129) Control No: 22543
Status: Design
Right-of-way:
Construction Timing: 06/02/2025 - 10/31/2025

## Slide 94: Union – Murray Project Number: NH-34-7(129) Control No: 22543
Anticipated Utilities Impact:
  Bridge Repair/Replace
Anticipated Request from Utilities:
  Provide Existing Locations
  Coordination with NDOT
Additional Information:
Utilities Involved:
  Cass County Rural Water District #1
  Lumen
  Nebraska Public Power District
  Nustar Pipeline
  Omaha Public Power District
  OneOK
  Village of Murray
  Village of Union
  Windstream Communications
  Zayo Group

## Slide 95: Union – Murray Project Number: NH-34-7(129) Control No: 22543

## Slide 96: US-75 & North 48th Street Project Number: NH-75-2(191) Control No: 22874
Project Length: 0.13
Scope of Work:
  Culvert Extension/Replacement
  Grading
  Access X-ings & Shoo-Fly

## Slide 97: US-75 & North 48th Street Project Number: NH-75-2(191) Control No: 22874
Status: Design
Right-of-way:
Construction Timing: 9/1/2025 - 11/7/2025

## Slide 98: US-75 & North 48th Street Project Number: NH-75-2(191) Control No: 22874
Anticipated Utilities Impact:
  Culvert Extension/Replace
  Grading
  Access X-ing
Anticipated Request from Utilities:
  Provide Existing Locations
  Potholing Required
Additional Information:
Utilities Involved:
  Cox Communications
  Lumen
  Metropolitan Utilities District
  Omaha Public Power District
  Washington Co. Rural Water District #1

## Slide 99: US-75 & North 48th Street Project Number: NH-75-2(191) Control No: 22874

## Slide 100: 156th St. – 132nd St., Omaha Project Number: NH-6-7(189) Control No: 22812
Project Length: 2.62
Scope of Work:
  Full Depth Pavement
  Grading
  Culvert Extension/Replacement

## Slide 101: 156th St. – 132nd St., Omaha Project Number: NH-6-7(189) Control No: 22812
Status: Design
Right-of-way:
Construction Timing: 4/28/2025 - 11/8/2025

## Slide 102: 156th St. – 132nd St., Omaha Project Number: NH-6-7(189) Control No: 22812
Anticipated Utilities Impact:
  Full Depth Pavement
  Urban Recon
  Grading
Anticipated Request from Utilities:
  Provide Existing Locations
  Potholing Required
  Coordination with NDOT
Additional Information:
Utilities Involved:
  AT&T Communications
  City of Omaha
  Cox Communications
  Lumen
  Metropolitan Utilities District
  Omaha Public Power District
  Pinpoint Communications
  Segra
  Verizon
  Windstream Communications

## Slide 103: 156th St. – 132nd St., Omaha Project Number: NH-6-7(189) Control No: 22812

## Slide 104: US-275/72nd St. Interchange Project Number: NH-275-7(194) Control No: 22469
Project Length: 0.62
Scope of Work:
  Urban Reconstruction
  Full Depth Pavement
  Grading

## Slide 105: US-275/72nd St. Interchange Project Number: NH-275-7(194) Control No: 22469
Status: Design
Right-of-way:
Construction Timing: 9/15/2025 - 11/25/2026

## Slide 106: US-275/72nd St. Interchange Project Number: NH-275-7(194) Control No: 22469
Anticipated Utilities Impact:
  Full Depth Pavement
  Urban Recon
  Grading
Anticipated Request from Utilities:
Additional Information:
Utilities Involved:
  AT&T Communications
  City of Omaha
  City of Ralston
  Cox Communications
  Great Plains Communications
  Lumen
  Verizon
  Metropolitan Utilities District
  Northern Natural Gas
  Omaha Public Power District
  Papio-Missouri Natural Resources District
  Pinpoint Communications
  Segra

## Slide 107: US-275/72nd St. Interchange Project Number: NH-275-7(194) Control No: 22469