## Slide 1: Utility program
District 3 Breakout Session

## Slide 2: This Meeting is Being Recorded
Notes: HDR

## Slide 3: Welcome
Before we begin, let’s have a brief safety moment.
Virtual Attendees
Unmute yourself or use your chat box if you are in an emergency situation.
In-Person Attendees
Emergency Exits
Tornado Shelter
911 Caller
AED Location
Restrooms
Notes: HDR

## Slide 4: Agenda
Introductions
High Impact Project Review (by construction year)
Communication and Coordination
Questions and Wrap Up
Notes: HDR

## Slide 5: Introductions
Notes: All speakers introduce themselves briefly (Dave, section head, HDR facilitators); Attendees can introduce themselves if it’s a small group. If not – skip it!

## Slide 6: 2024 Utility policy
NDOT rolled out a new utility accommodation policy in 2024.
You can find more information, as well as a webinar about the changes, on the NDOT utility website at https://dot.nebraska.gov/business-center/utilities/.

## Slide 7: Outstanding Cy 2025
The following projects will likely not be completed in 2025

## Slide 8: Columbus South Bridges Project Number: NH-30-5(131) Control No: 31983
Project Length: 0.00
Scope of Work:
  Bridge Replacement
  Bridge Repair
  Guardrail

## Slide 9: Columbus South Bridges Project Number: NH-30-5(131) Control No: 31983
Status: Construction
Right-of-way: Completed
Construction Timing: 4/1/2025 - 11/30/2027

## Slide 10: Columbus South Bridges Project Number: NH-30-5(131) Control No: 31983
Anticipated Utilities Impact:
  Bridge Repair/Replace
Anticipated Request from Utilities:
Additional Information:
  No K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Allo Communications
  Black Hills Energy
  City of Columbus
  Frontier Communications
  Great Plains Communications
  Loup River Public Power District
  Lumen

## Slide 12: Monroe East & West (MS) Project Number: STP-22-5(119) Control No: 32292
Project Length: 13.20
Scope of Work:
  Bridge Replacement
  Grading
  Bridge Repair

## Slide 13: Monroe East & West (MS) Project Number: STP-22-5(119) Control No: 32292
Status: Construction
Right-of-way: Completed
Construction Timing: 3/24/2025 - 10/17/2026

## Slide 14: Monroe East & West (MS) Project Number: STP-22-5(119) Control No: 32292
Anticipated Utilities Impact:
  Bridge Repair/Replace
  Grading
  New ROW
Anticipated Request from Utilities:
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Cornhusker Public Power District
  Frontier Communications
  OneOK
  Loup River Public Power District
  Northeast Nebraska Telephone Company
  Village of Monroe

## Slide 16: N-57 - East Jct N-15 Project Number: TIB-275-6(149) Control No: 32319A
Project Length: 11.78
Scope of Work:
  Grading
  Full Depth Pavement

## Slide 17: N-57 - East Jct N-15 Project Number: TIB-275-6(149) Control No: 32319A
Status: Construction
Right-of-way: In Progress
Construction Timing: 4/1/2025 - 11/30/2027

## Slide 18: N-57 - East Jct N-15 Project Number: TIB-275-6(149) Control No: 32319A
Anticipated Utilities Impact:
  New Alignment
  Grading
  New ROW
Anticipated Request from Utilities:
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy
  Cuming County Public Power District
  Great Plains Communications
  Lumen
  Stanton County Public Power District
  Stanton Telecommunications

## Slide 19: Niobrara East & West Project Number: S-12-5(1011) Control No: 31674
Project Length: 10.64
Scope of Work:
  Grading
  Full Depth Pavement
  Guardrail
Notes: + separate streambank project

## Slide 20: Niobrara East & West Project Number: S-12-5(1011) Control No: 31674
Status: Construction
Right-of-way: In Progress
Construction Timing: 9/1/2025 - 7/31/2029

## Slide 21: Niobrara East & West Project Number: S-12-5(1011) Control No: 31674
Anticipated Utilities Impact:
  New Alignment
  Grading
  New ROW
Anticipated Request from Utilities:
Additional Information:
  K-Sheets Required
  Special Provisions Required
  Related Wetland Bank project
Utilities Involved:
  Great Plains Communications
  North Central Public Power District
  Santee Tribe
  U.S. Army Corps of Engineers
  Village of Niobrara

## Slide 23: Macy Intersection Project Number: DPS-75-4(118) Control No: 32415
Project Length: 0.00
Scope of Work:
  Grading
  Full Depth Pavement
  Access X-ings & Shoo-Fly

## Slide 24: Macy Intersection Project Number: DPS-75-4(118) Control No: 32415
Status: Design
Right-of-way: In Progress
Construction Timing: 5/1/2025

## Slide 25: Macy Intersection Project Number: DPS-75-4(118) Control No: 32415
Anticipated Utilities Impact:
  New Alignment
  Grading
  New ROW
Anticipated Request from Utilities:
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:

## Slide 27: Cy 2026
The following projects are anticipated to be let during 2026

## Slide 28: East Jct N-15 - Wisner Project Number: TIB-275-6(150) Control No: 32319B
Project Length: 4.21
Scope of Work:
  Grading
  Full Depth Pavement

## Slide 29: East Jct N-15 - Wisner Project Number: TIB-275-6(150) Control No: 32319B
Status: Design
Right-of-way: In Progress
Construction Timing: 10/27/2025 - 11/30/2028

## Slide 30: East Jct N-15 - Wisner Project Number: TIB-275-6(150) Control No: 32319B
Anticipated Utilities Impact:
  Grading
  Temp. Roads/Drives
  New ROW
Anticipated Request from Utilities:
  Provide Existing Locations
  Utilities Workshop
  Provide Existing Locations
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  City of Wisner Water
  Cuming County Public Power District
  Cuming County Rural Water District 1
  Great Plains Communications
  Lumen
  Tallgrass Energy

## Slide 32: District 3 High Mast Tower Replacement Project Number: STP-129-1(32) Control No: 32417
Project Length:
Scope of Work:

## Slide 33: District 3 High Mast Tower Replacement Project Number: STP-129-1(32) Control No: 32417
Status: Design
Right-of-way: Not Required
Construction Timing: 5/18/2026 - 10/31/2026

## Slide 34: District 3 High Mast Tower Replacement Project Number: STP-129-1(32) Control No: 32417
Anticipated Utilities Impact:
Anticipated Request from Utilities:
Additional Information:
Utilities Involved:
  Dakota County Rural Water District
  Fiber Communications
  Great Plains Communications
  Long Lines Broadband
  Mid American Energy
  Nebraska Public Power District
  South Sioux City
  Sparklight Internet
  Verizon

## Slide 36: Wisner- West Point North Project Number: S-275-6(1062) Control No: 32024A
Project Length: 12.21
Scope of Work:
  Grading
  Full Depth Pavement

## Slide 37: Wisner- West Point North Project Number: S-275-6(1062) Control No: 32024A
Status: Design
Right-of-way: In Progress
Construction Timing: 4/1/2026 - 10/31/2027

## Slide 38: Wisner- West Point North Project Number: S-275-6(1062) Control No: 32024A
Anticipated Utilities Impact:
  Grading
  New Alignment
  New ROW
Anticipated Request from Utilities:
  Provide Existing Locations
  Potholing Required
  Coordination with NDOT
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy
  City of Wisner
  Cuming County Public Power District
  Great Plains Communications
  Lumen
  Skywave Wireless
  Sparklight
  Tallgrass Energy
  Village of Beemer
  Cuming County Rural Water District

## Slide 40: cy 2027
The following projects are anticipated to be let during 2027

## Slide 41: Elgin - Neligh Project Number: STP-14-4(119) Control No: 32383
Project Length: 10.80
Scope of Work:
  Culvert Extension/Replacement
  Bridge Repair

## Slide 42: Elgin - Neligh Project Number: STP-14-4(119) Control No: 32383
Status: Design
Right-of-way: In Progress
Construction Timing: 4/12/2027 - 11/24/2027

## Slide 43: Elgin - Neligh Project Number: STP-14-4(119) Control No: 32383
Anticipated Utilities Impact:
  Temp. Roads/Drives
  New ROW
Anticipated Request from Utilities:
  Provide Existing Locations
  Utilities Workshop
  Provide Existing Locations
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy
  City of Elgin
  City of Neligh
  Elkhorn Rural Public Power District
  Frontier Communications
  Great Plains Communications
  Lumen
  Midstates Data Transport
  OPTK Networks
  Northeast Nebraska Telephone Company
  Tallgrass Energy

## Slide 45: Fordyce East & West Project Number: STP-HSIP-12-6(120) Control No: 32382
Project Length: 9.20
Scope of Work:
  Culvert Extension/Replacement
  Bridge Repair
  Grading

## Slide 46: Fordyce East & West Project Number: STP-HSIP-12-6(120) Control No: 32382
Status: Design
Right-of-way: In Progress
Construction Timing: 4/1/2027-10/31/2027

## Slide 47: Fordyce East & West Project Number: STP-HSIP-12-6(120) Control No: 32382
Anticipated Utilities Impact:
Anticipated Request from Utilities:
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Cedar Knox Rural Water District
  Cedar Knox Public Power District
  Great Plains Communications
  Hartington Telecommunications
  Lumen
  Nustar Pipeline
  TransCanada Keystone Pipeline
  Village of Fordyce

## Slide 49: Clearwater West Project Number: NH-275-5(147) Control No: 32387
Project Length: 6.49
Scope of Work:
  Culvert Extension/Replacement
  Resurfacing

## Slide 50: Clearwater West Project Number: NH-275-5(147) Control No: 32387
Status: Design
Right-of-way: In Progress
Construction Timing: 8/9/2027 - 11/24/2027

## Slide 51: Clearwater West Project Number: NH-275-5(147) Control No: 32387
Anticipated Utilities Impact:
Anticipated Request from Utilities:
Additional Information:
Utilities Involved:
  Black Hills Energy
  Elkhorn Rural Public Power District
  Great Plains Communications
  Lumen
  Northeast Nebraska Telephone Company
  Tallgrass Energy

## Slide 52: Clearwater West Project Number: NH-275-5(147) Control No: 32387

## Slide 53: Jct. US-81/ N-12 Intersection Project Number: HSIP-81-4(130) Control No: 32409
Project Length: 0.00
Scope of Work:
  Full Depth Pavement
  Culvert Extension/Replacement
  ITS/Lighting

## Slide 54: Jct. US-81/ N-12 Intersection Project Number: HSIP-81-4(130) Control No: 32409
Status: Design
Right-of-way: In Progress
Construction Timing: 7/12/2027 - 11/6/2027

## Slide 55: Jct. US-81/ N-12 Intersection Project Number: HSIP-81-4(130) Control No: 32409
Anticipated Utilities Impact:
Anticipated Request from Utilities:
Additional Information:
Utilities Involved:
  Cedar Knox Rural Water District
  Great Plains Communications
  Lumen

## Slide 57: Neligh to Tilden Project Number: NH-275-5(146) Control No: 32381
Project Length: 12.35
Scope of Work:
  Full Depth Pavement
  Bridge Replacement
  Bridge Repair

## Slide 58: Neligh to Tilden Project Number: NH-275-5(146) Control No: 32381
Status: Design
Right-of-way: In Progress
Construction Timing: 3/29/2027 - 11/22/2028

## Slide 59: Neligh to Tilden Project Number: NH-275-5(146) Control No: 32381
Anticipated Utilities Impact:
Anticipated Request from Utilities:
Additional Information:
Utilities Involved:
  Black Hills Energy
  City of Neligh
  City of Tilden
  Elkhorn Rural Public Power District
  Frontier Communications
  Great Plains Communications
  Lumen
  Midstates Data Transport
  Nebraska Public Power District
  Tallgrass Energy
  Village of Oakdale

## Slide 60: Neligh to Tilden Project Number: NH-275-5(146) Control No: 32381

## Slide 61: Madison East Project Number: STP-32-5(110) Control No: 32405
Project Length: 11.97
Scope of Work:
  Mill and Fill
  Box Culvert Repairs
  Bridge Repairs with Guardrail Replacement

## Slide 62: Madison East Project Number: STP-32-5(110) Control No: 32405
Status: Design
Right-of-way: N/A
Construction Timing: 7/19/2027 - 11/24/2027

## Slide 63: Madison East Project Number: STP-32-5(110) Control No: 32405
Anticipated Utilities Impact:
Anticipated Request from Utilities:
Additional Information:
Utilities Involved:
  Black Hills Energy
  City of Madison
  Elkhorn Rural Public Power District
  Frontier Communications
  Midstates Data Transport
  Nebraska Public Power District
  Sparklight
  Stanton Telecommunications

## Slide 64: Questions & Wrap Up
Notes: HDR

## Slide 65: Any final Questions?
Ask them now!
If you have questions after this meeting, or would like to view more detailed project maps, please reach out to your utility coordinator.
Notes: HDR

## Slide 66: Have a Question about a project your Utility is involved in?
Contact your district’s utility coordinator!
Notes: HDR

## Slide 67: We need your feedback
Your valuable feedback helps these meetings – and NDOT’s utility coordination program – be better.
Use your phone’s camera to scan this QR code or use our paper survey.
Notes: HDR

## Slide 68: Visit our Website
Visit NDOT.info/utility for more information on:
Utility accommodation
Permitting
Coordination
Project information
Reimbursements
Additional information
Scan the QR Code to view the 2026 Program Book!
Notes: HDR

## Slide 69: Thank You
Notes: HDR

## Slide 70: In Stanton & North Project Number: STP-57-3(111) Control No: 32359
Project Length: 5.03
Scope of Work:
  Resurfacing
  Shoulder Work
  Grading

## Slide 71: In Stanton & North Project Number: STP-57-3(111) Control No: 32359
Status: Preparing for Bid
Right-of-way: Completed
Construction Timing: 3/24/2025 - 11/26/2025

## Slide 72: In Stanton & North Project Number: STP-57-3(111) Control No: 32359
Anticipated Utilities Impact:
  Grading
  Culvert Extension/Replace
Anticipated Request from Utilities:
Additional Information:
  K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Black Hills Energy
  City of Stanton
  Great Plains Communications
  Lumen
  Sparklight Internet
  Stanton County Public Power District
  Stanton Telecommunications
  Tallgrass Energy

## Slide 73: In Norfolk Traffic Signals (LET) Project Number: HSIP-81-3(150) Control No: 32363
Project Length: 5.32
Scope of Work:
  Miscellaneous

## Slide 74: In Norfolk Traffic Signals (LET) Project Number: HSIP-81-3(150) Control No: 32363
Status: Design
Right-of-way: Not Required
Construction Timing: 7/7/2025 - 11/1/2025

## Slide 75: In Norfolk Traffic Signals (LET) Project Number: HSIP-81-3(150) Control No: 32363
Anticipated Utilities Impact:
Anticipated Request from Utilities:
Additional Information:
  No K-Sheets Required
  Special Provisions Required
Utilities Involved:
  Allo Communications
  Black Hills Energy
  City of Norfolk
  Lumen
  Midstates Data Transport
  Nebraska Department of Water, Energy, and Environment
  Nebraska Public Power District
  NuStar Pipeline
  Pierce Telephone Company
  Sparklight Internet
  Segra
  USCOC N-K

## Slide 76: In Norfolk Traffic Signals (LET) Project Number: HSIP-81-3(150) Control No: 32363