## Directions
Directions for Completing Progress Report
** HIDE TAB / DO NOT PRINT **
Purpose
This document outlines the requirements and expectations for submitting progress reports. This document is intended as a guidance document only, refer to EXECUTED AGREEMENT, Fees and Payments Exhibit - Section 7 Invoices and Progress Reports.
General Guidelines
Submission Deadlines
• Refer to agreement, Fees and Payments Exhibit - Section 7. A
• Consultant shall submit invoices to State based on Consultant’s billing period but shall not submit more than one invoice per month.
• State will not pay for costs incurred, but not submitted to State within 180 days of the date incurred
Submission Method
• All invoices and progress reports shall be submitted via OnBase

## Full Build
To: | Insert Name of NDOT Consultant Coordinator
From: | Insert Name Consultant Project Manager, Name of Company
Project: | Insert Project Name
Control No: | Insert NDOT Control Number
Billing Period: | Insert Month Day, Year to Month Day, Year
** HIDE ROW / DO NOT PRINT ** Provide bulleted list of existing executed agreements or work orders
EXECUTED AGREEMENTS AND WORK ORDERS
• Example 1…Notice to Proceed for initial setup, review and preliminary survey was issued by the NDOT effective Month Day, Year. Example 2 ...Notice to Proceed for Supplement No. 1 for environmental services, preliminary roadway and bridge design was issued by the NDOT Month Day, Year. • Example 3 ...Notice to Proceed for Work Order for expanded topographic survey was issued by the NDOT effective Month Day, Year. • Example 4 ...Notice to Proceed for Supplement No. 3 for Final Roadway and Bridge Design was issued by the NDOT effective Monty Day, Year.
** HIDE ROW / DO NOT PRINT ** For each APPLICABLE Task or Subtask(Bridge & Environmental): • Provide bulleted list of work performed this billing period. • Provide bulleted list of work anticipated for the next billing period. • Provide bulleted list of information needed from others to complete task. • Provide bulleted list of identified out of scope work that has been communicated to appropriate NDOT staff for review and approval of either a Supplement or Work Order. This is for work in which Consultant has not been issued an NTP and should NOT proceed until an NTP is issued. ** HIDE ROWS / DO NOT PRINT ALL TASKS / SUBTASKS NOT APPLICALE TO THIS AGREEMENT** ** NOTE ALL TASKS / SUBTASKS PERFORMED BY SUBCONSULTANT - REFER TO SUBCONSULTANT PROGRESS REPORT**
PROJECT MANAGEMENT
Work Performed
• Insert text here
Anticipated Work Next Period
• Insert text here
Information Needed
• Insert text here
Identified Out of Scope Work - Pending Approval
• Insert text here
SURVEY
Work Performed
• Example - Completed field survey for corridor, including topographic and boundary data collection. • Example - Compiled and drafted base mapping for design based on collected survey data.
Anticipated Work Next Period
• Example - Complete supplemental cross-sections at bridge approach. • Example - Update base map with recent utility locates and field changes.
Information Needed
• Example - Need NTP to begin pick up survey for new drives at east end of project
ROADWAY DESIGN SERVICES
Initial Project Review and Setup
Work Performed
• Example - Reviewed preliminary alignment alternatives and coordinated with NDOT for design criteria confirmation.
Anticipated Work Next Period
• Insert text here
Information Needed
• Insert text here
Design Phase
Work Performed
• Example - Developed horizontal and vertical alignments and prepared 30% design plans.
Anticipated Work Next Period
• Example - Submit Pre-PIH submittal, AASHTOWare quantities, forms and plans.
Information Needed
• Insert text here
Plan Details Phase
Work Performed
• Insert text here
Anticipated Work Next Period
• Insert text here
Information Needed
• Example - Need completed pick up survey to finalize LOCs for right of way
Plans Package Phase (Pre-PS&E)
Work Performed
• Example - Prepared final plan package for PSE review, incorporating QA/QC feedback.
Anticipated Work Next Period
• Insert text here
Information Needed
• Insert text here
PS&E Plans Package (Final)
Work Performed
• Example - Finalized sealed construction plans and submitted full PSE package to NDOT.
Anticipated Work Next Period
• Insert text here
Information Needed
• Insert text here
RIGHT-OF-WAY
Work Performed
• Insert text here
Anticipated Work Next Period
• Insert text here
Information Needed
• Insert text here
BRIDGE SERVICES
Bridge Design
Work Performed
• Example - Confirmed span arrangement and lengths • Example - Coordinated vertical profile with Roadway • Example - Completed TS&L plans and design data sheets for single-span girder bridge. • Example - Finalized bridge hydraulics design and submitted TS&L package for culvert crossing. • Example - Completed structural calculations and detail sheets; ready for incorporation into final plans.
Anticipated Work Next Period
• Example - Begin girder design • Example - Begin preparation of girder detail • Example - Prepare structural section views for plan details phase. • Example - Submit design assumptions and hydraulic modeling for review. • Example - Incorporate utility conflicts and final review comments into plans.
Information Needed
• Insert text here
Bridge Repair
Work Performed
• Insert text here
Anticipated Work Next Period
• Insert text here
Information Needed
• Insert text here
Bridge Hydraulics
Work Performed
• Insert text here
Anticipated Work Next Period
• Insert text here
Information Needed
• Insert text here
ENVIRONMENTAL SERVICES
CE Document Tasks
Work Performed
• Example - Prepared status update email for NDOT and requested status of PI documentation. • Example - Began development of the CE. • Example - Updated CE with wetland PQS information. • Example - Compiled draft CE with attachments, conducted internal QC, and made revisions. • Example - Revised CE per NDOT comments and resubmitted. • Example - Coordinated with NDOT NEPA Specialist regarding the anticipated type of 4(f) use.
Anticipated Work Next Period
• Example - Continue development of the CE.
Information Needed
• Insert text here
T&E Review
Work Performed
• Example - Conducted bat surveys and prepared survey forms.
Anticipated Work Next Period
• Example - Finish drafting Biological Assessment and submit BA to NDOT.
Information Needed
• Insert text here
Hazmat Materials Review
Work Performed
• Example - None this billing period. • Example - Completed initial hazmat review and entered information into NEDS. • Example - Coordinated with NDOT hazmat specialist and revised HMR in NEDS per NDOT comments.
Anticipated Work Next Period
• Example - Continue development of the HMR.
Information Needed
• Insert text here
Wetland Delineation
Work Performed
• Example - Prepared maps and forms for upcoming field work. • Example - Completed wetland delineation field work. • Example - Prepared gdb and submitted to NDOT. • Example - Began drafting the delineation report. • Example - Drafted wetland delineation report and initiated internal QC. • Example - Revised delineation report based on expanded study area.
Anticipated Work Next Period
• Example - Update Wetland Delineation Report based on expanded study area • Example - Continue development of the Wetland report.
Information Needed
• Insert text here
404 Permit
Work Performed
• Example - Drafted PCN to the extent possible without the remaining T&E and 106 PQS memos, and submitted to NDOT for preliminary review. • Example - Revised PCN in response to NDOT comments.
Anticipated Work Next Period
• Insert text here
Information Needed
• Insert text here
Section 106
Work Performed
• Example - Survey completed and results provided to NDOT. • Example - Submitted draft APE.
Anticipated Work Next Period
• Insert text here
Information Needed
• Insert text here
Noise Study
Work Performed
• Example - Coordinated with NDOT to obtain traffic information. • Example - Completed noise modeling and began drafting report.
Anticipated Work Next Period
• Example - Submit report for NDOT review.
Information Needed
• Example - Section 4(f) Properties Identification documentation Floodplain PQS memo T&E PQS Awaiting confirmation from design as to whether or not X location will be added to the project Need updated project description Need a supplement to do acoustic survey on the viaduct
PUBLIC INVOLVEMENT
Work Performed
• Example - Submitted DRAFT Public Involvement Plan and Schedule for NDOT approval • Example - Finalized and sent responses to public comment
Anticipated Work Next Period
• Example - Submit Final Public Involvement Summary and Report
Information Needed
• Insert text here
UTILITIES
Work Performed
• Insert text here
Anticipated Work Next Period
• Insert text here
Information Needed
• Insert text here
TRAFFIC
Work Performed
• Insert text here
Anticipated Work Next Period
• Insert text here
Information Needed
• Insert text here
ITS/LIGHTING DESIGN
Work Performed
• Insert text here
Anticipated Work Next Period
• Insert text here
Information Needed
• Insert text here
CONSTRUCTION SERVICES
Work Performed
• Example - Responded to 2 RFIs - NU 1800 Mesh - Bridge Electrical Conduit & Junction Boxes • Example - Reviewed 2 shop drawings - Sheet Pile - Pedestrian Railing
Anticipated Work Next Period
• Example - Review shop drawings and address RFIs as requested
Information Needed
• Insert text here