## Example
EXAMPLE OVERHEAD/INDIRECT COST RATE (ICR) TRUE-UP CALCULATIONS
v.2018.1024 | [6 empty] | EXAMPLE Cost Breakdown Form | [5 empty] | FYE |  | OH Rate | FCCM
[12 empty] | OH Rates: | 2014-09-30 |  | 161.1% | 0.76%
| Consultant Name: | Nebraska Consultants, Inc. | [10 empty] | 2015-09-30 |  | 150.4% | 0.58%
| Agreement #: | BK1583 | [10 empty] | 2016-09-30 |  | 153.2% | 0.32%
| Date: | 2017-12-18 | [10 empty] | 2017-09-30 |  | 157.8% | 0.39%
| Purpose of Adjustment: | Closeout of Agreement
|  |  | A |  | B | C | D | E | F | G | H | I | J | K | L | M | N | P | R
Invoice Number | Invoice Date | Dates of Labor | Direct Labor Amount |  | Invoiced Overhead Rate (%) | Invoiced Overhead Amount | Profit/ Fee Rate (%) | Invoiced Profit/Fee Amount | Invoiced FCCM Rate (%) | Invoiced FCCM Amount | Invoiced Total Amount | Approved Overhead Rate | Approved Overhead Amount | Profit/ Fee Rate (%) | Approved Profit/Fee Amount | Approved FCCM Rate (%) | Approved FCCM Amount | Approved Total Amount | Calculated Adjustment Amount
[6 empty] | A*B |  | (A+C)*D |  | A*F | A+C+E+G |  | A*I |  | (A+J)*K |  | A*M | A+J+L+N | P-H
1 | 2016-03-24 | 01/1/16 - 3/18/16 | 1157.9 |  | 161.1% | 1865.1453 | 12.8% | 386.9498 | 0.76% | 8.8 | 3418.7952 | 153.2% | 1774.0186 | 12.8% | 375.2856 | 0.32% | 3.7053 | 3310.9094 | -107.8857
2 | 2016-06-01 | 3/19/16 - 5/22/16 | 8773.83 |  | 150.4% | 13193.2082 | 12.8% | 2811.7809 | 0.58% | 50.8882 | 24829.7073 | 153.2% | 13442.3849 | 12.8% | 2843.6755 | 0.32% | 28.0763 | 25087.9667 | 258.2594
3 | 2016-08-03 | 5/23/16 - 7/31/16 | 8413.21 |  | 150.4% | 12650.9439 | 12.8% | 2696.2117 | 0.58% | 48.7966 | 23809.1622 | 153.2% | 12889.879 | 12.8% | 2726.7954 | 0.32% | 26.9223 | 24056.8067 | 247.6445
4 | 2016-10-04 | 8/1/16 - 9/30/16 | 14011.71 |  | 150.4% | 21069.4083 | 12.8% | 4490.3831 | 0.58% | 81.2679 | 39652.7694 | 153.2% | 21467.3409 | 12.8% | 4541.3185 | 0.32% | 44.8375 | 40065.2069 | 412.4375
5 | 2016-07-28 | 10/01/16 - 11/30/16 | 2246.17 |  | 150.4% | 3377.5658 | 12.8% | 719.8382 | 0.58% | 13.0278 | 6356.6018 | 157.8% | 3545.1301 | 12.8% | 741.2864 | 0.39% | 8.7601 | 6541.3466 | 184.7448
6 | 2016-08-24 | 12/1/16 - 12/31/16 | 1477.51 |  | 150.4% | 2221.7318 | 12.8% | 473.5029 | 0.58% | 8.5696 | 4181.3143 | 157.8% | 2331.954 | 12.8% | 487.6114 | 0.39% | 5.7623 | 4302.8377 | 121.5234
7 | 2017-04-01 | 1/1/17 - 3/31/17 | 232.66 |  | 150.4% | 349.8508 | 12.8% | 74.5614 | 0.58% | 1.3494 | 658.4217 | 157.8% | 367.2073 | 12.8% | 76.783 | 0.39% | 0.90737 | 677.5577 | 19.136
8 | 2017-07-03 | 4/1/17 - 6/30/17 | 3233.56 |  | 153.2% | 4954.1373 | 12.8% | 1048.0253 | 0.32% | 10.3474 | 9246.0699 | 157.8% | 5103.5277 | 12.8% | 1067.1472 | 0.39% | 12.6109 | 9416.8459 | 170.7759
9 | 2017-10-12 | 7/1/17 - 9/30/17 | 865.13 |  | 153.2% | 1325.4657 | 12.8% | 280.3962 | 0.32% | 2.7684 | 2473.7603 | 157.8% | 1365.4347 | 12.8% | 285.5123 | 0.39% | 3.374 | 2519.451 | 45.6906
10 | 2017-12-01 | 10/1/17 - 11/30/17 | 321.87 |  | 153.2% | 493.137 | 12.8% | 104.3209 | 0.32% | 1.03 | 920.3579 | 157.8% | 508.0074 | 12.8% | 106.2243 | 0.39% | 1.2553 | 937.357 | 16.9991
[6 empty] | 0 |  | 0 |  | 0 | 0 |  | 0 | 0% | 0 |  | 0 | 0 | 0
[6 empty] | 0 |  | 0 |  | 0 | 0 |  | 0 | 0% | 0 |  | 0 | 0 | 0
[6 empty] | 0 |  | 0 |  | 0 | 0 |  | 0 | 0% | 0 |  | 0 | 0 | 0
[6 empty] | 0 |  | 0 |  | 0 | 0 |  | 0 | 0% | 0 |  | 0 | 0 | 0
TOTALS |  |  | 40733.55 |  |  | 61500.5941 |  | 13085.9704 |  | 226.8454 | 115546.9599 |  | 62794.8847 |  | 13251.6396 |  | 136.2112 | 116916.2856 | 1369.3256
Calculated Adjustment
|  | Adjustment to Overhead (Jt - Ct): | 1294.2906 | Underbilled |  |  | Note: | Consultant's Invoice for underbilled amounts is subject to Agreement limitations and may be reduced below Calculated Adjustment amounts
|  | Adjustment to Fixed Fee (Lt - Et): | 165.6692 | Underbilled
|  | Adjustment to Facility Capital (Nt - Gt): | -90.6342 | Overbilled
|  | Total Amount: | 1369.3256 | Underbilled

## Example Cost Breakdown Form
Cost Breakdown Form
for Actual Cost Plus Fixed Fee (CPFF) Agreements
Company Name: |  |  |  | Nebraska Consultants, Inc.
Control No.: | [5 empty] | Project No.:
Project Location:
AFE No.: |  |  |  | n/a
Agreement No.: |  |  |  | BK1583 |  | Expire Date: | 2019-12-12
Invoice No.: |  |  |  | 11.0 (OH Adj) |  | Invoice Date: | 2017-12-18
% Work Completed: |  |  |  | 100%
Current Billing Period: |  |  |  | 2016-01-01 | thru | 2017-11-30
| AGR # | BK1583 |  | Direct Labor Costs |  | All Other Costs | Max Fixed Fee (Profit) | Total Contract Amount
Amount thru sup # |  |  | 0 | 42100.52 |  | 81813.47 | 13239.25 | 137153.24
Amount
[6 empty] | This Period | Previously Billed | To Date
Direct Labor Costs | [6 empty] | 40733.55 | 40733.55
|  | Overhead @ | 153.2% | of direct labor |  | 0 | 61500.59 | 61500.59
|  | Fixed Fee @ | 12.8% | of labor+overhead |  | 0 | 13085.97 | 13085.97
|  | FCCM @ | 0.32% | of direct labor |  | 0 | 226.85 | 226.85
0
Direct Costs (Non-Labor) | [6 empty] | 1254.86 | 1254.86
Outside Services (Subconsultants):
| Name |  |  | Max Amount
0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
0
Adjustments:
| Overhead |  |  |  |  | 1294.29 |  | 1294.29
| Fixed Fee for profit |  |  |  |  | 153.279 |  | 153.279
| FCCM |  |  |  |  | -90.63 |  | -90.63
| Other: | [6 empty] | 0
Total Amount DUE >> | [5 empty] | 1356.939 | 116801.82 | 118158.759
By submitting this form electronically to State, Consultant certifies submitted costs are actual and allowed by contract. | [6 empty] | Total Agreement Amount Remaining: | 18994.481
[7 empty] | Total Fixed Fee Remaining: | 0.001
Note: In this example, all of the Fixed Fee adjustment could not be billed due to limitation in Agreement.